## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
Cyber Essentials sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Overview
Cyber Essentials Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
Cyber Essentials ¦ Version 1.0 ¦ Sequenced implementation roadmap
Section | Detail
Framework | Cyber Essentials
Version | 1.0
Purpose | Practical rollout plan for implementing the pack as a working operating model.
How to use | Adapt owners, sequencing, and notes to the customer environment while keeping the implementation logic intact.
Key pack assets | Secure Configuration Policy; User Access Management Procedure; Asset Register; Access Request Form
Roadmap notes | Turn the pack into a practical baseline-security rollout rather than a certification-only exercise. ¦ The pack supports governance and evidence planning; customer technical implementation is still required.

## Roadmap
Cyber Essentials Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
Cyber Essentials ¦ Version 1.0 ¦ Sequenced implementation roadmap
Phase / Timeframe | Priority | Workstream | Task | Related Documents | Expected Output | Suggested Owner | Evidence to Retain | Status | Notes
Foundation / Scope / Governance | High | Device and Service Baseline | Confirm the device estate, internet-facing services, admin exposure, and ownership for the core control themes. | Secure Configuration Policy | Current baseline view and control owners | IT Lead / Management | Device inventory, service list, owner assignments, scope notes | Not Started | Keep the first scope simple and realistic.
Core Policy Approval | High | Security Baseline | Approve the policy baseline for secure configuration, firewalling, access control, malware protection, and patching. | Secure Configuration Policy | Approved Cyber Essentials policy baseline | IT Lead / Management | Approvals, version-controlled policies, issue log | Not Started | Only approve what teams can actually operate day to day.
Operational Procedure Adoption | High | Working Practice | Adopt the procedures that make the baseline real, including user access management, patch handling, hardening, backup, and incidents. | User Access Management Procedure | Operational procedures and clear owner expectations | IT Lead / Operations | Procedure sign-off, admin review records, patch workflow outputs | Not Started | Prioritise admin access, MFA, and patching discipline.
Register and Evidence Setup | High | Evidence Readiness | Collect the core evidence set for patching, device security, malware protection, firewall review, and access control. | Asset Register | Simple evidence pack and review rhythm | IT Lead | Patch reports, access review outputs, anti-malware status, firewall review notes | Not Started | Evidence should be quick to update and understandable to management.
Review / Validation / Readiness | High | Certification Readiness | Run a practical self-review against the control themes and close the highest-value gaps. | Asset Register | Readiness review, remediation list, and recurring maintenance rhythm | Management / IT Lead | Review notes, remediation tracker, updated baseline records | Not Started | Challenge whether the documented controls match the technical reality.

## Owners_and_Evidence
Cyber Essentials Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
Cyber Essentials ¦ Suggested ownership and evidence planning
Suggested Owner | Workstream | Task Focus | Related Documents | Expected Output | Evidence to Retain | Status
IT Lead / Management | Device and Service Baseline | Confirm the device estate, internet-facing services, admin exposure, and ownership for the core control themes. | Secure Configuration Policy | Current baseline view and control owners | Device inventory, service list, owner assignments, scope notes | Planned
IT Lead / Management | Security Baseline | Approve the policy baseline for secure configuration, firewalling, access control, malware protection, and patching. | Secure Configuration Policy | Approved Cyber Essentials policy baseline | Approvals, version-controlled policies, issue log | Planned
IT Lead / Operations | Working Practice | Adopt the procedures that make the baseline real, including user access management, patch handling, hardening, backup, and incidents. | User Access Management Procedure | Operational procedures and clear owner expectations | Procedure sign-off, admin review records, patch workflow outputs | Planned
IT Lead | Evidence Readiness | Collect the core evidence set for patching, device security, malware protection, firewall review, and access control. | Asset Register | Simple evidence pack and review rhythm | Patch reports, access review outputs, anti-malware status, firewall review notes | Planned
Management / IT Lead | Certification Readiness | Run a practical self-review against the control themes and close the highest-value gaps. | Asset Register | Readiness review, remediation list, and recurring maintenance rhythm | Review notes, remediation tracker, updated baseline records | Planned