## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
GDPR sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Overview
GDPR Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
GDPR ¦ Version 1.0 ¦ Sequenced implementation roadmap
Section | Detail
Framework | GDPR
Version | 1.0
Purpose | Practical rollout plan for implementing the pack as a working operating model.
How to use | Adapt owners, sequencing, and notes to the customer environment while keeping the implementation logic intact.
Key pack assets | Data Protection Policy; DSAR Procedure; Record of Processing Activities (RoPA); DSAR Request Form
Roadmap notes | Move from a document set to a practical privacy operating model. ¦ Governance and data understanding first, then procedures and evidence-backed review.

## Roadmap
GDPR Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
GDPR ¦ Version 1.0 ¦ Sequenced implementation roadmap
Phase / Timeframe | Priority | Workstream | Task | Related Documents | Expected Output | Suggested Owner | Evidence to Retain | Status | Notes
Foundation / Scope / Governance | High | Privacy Governance | Confirm privacy ownership and approve the core GDPR governance baseline. | Data Protection Policy | Approved privacy governance baseline | Management / Data Protection Lead | Approval records, owner assignments, governance notes | Not Started | Keep governance language aligned to the real processing model.
Foundation / Scope / Governance | High | Data Understanding | Identify what personal data is processed, for what purpose, and where the most material risk sits. | Record of Processing Activities (RoPA) | Initial processing inventory and risk picture | Data Protection Lead / Operations | ROPA entries, system notes, prioritised action list | Not Started | Start with the most material customer, employee, and marketing processes.
Core Policy Approval | High | Policy Baseline | Approve the policy baseline for protection, retention, rights handling, breach response, classification, and notices. | Data Protection Policy | Approved privacy policy baseline and outward-facing wording | Data Protection Lead / Management | Approvals, issue log, reviewed notice wording | Not Started | External notices must not drift away from internal practice.
Operational Procedure Adoption | High | Operational Privacy Controls | Adopt the procedures and templates for DSARs, breaches, retention, handling, and processor management. | DSAR Procedure; DSAR Request Form | Operational privacy workflows and escalation routes | Data Protection Lead / Functional Owners | Procedure sign-off, case handling records, workflow notes | Not Started | Pair the documentation with actual response discipline.
Register and Evidence Setup | High | Records and Logs | Populate the ROPA, breach log, data sharing register, and consent and notice records used for accountability. | Record of Processing Activities (RoPA) | Live accountability records and privacy evidence base | Data Protection Lead / IT / Marketing | Updated registers, notices, consent records, breach and request records | Not Started | Evidence should show what happens in practice.
Review / Validation / Readiness | High | Compliance Review | Review whether rights handling, breach triage, notices, retention, and processor oversight are operating consistently. | DSAR Procedure | Privacy review outputs and remediation actions | Data Protection Lead / Management | Review notes, sample case outputs, action tracker | Not Started | Use real cases and record samples to test maturity.

## Owners_and_Evidence
GDPR Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
GDPR ¦ Suggested ownership and evidence planning
Suggested Owner | Workstream | Task Focus | Related Documents | Expected Output | Evidence to Retain | Status
Management / Data Protection Lead | Privacy Governance | Confirm privacy ownership and approve the core GDPR governance baseline. | Data Protection Policy | Approved privacy governance baseline | Approval records, owner assignments, governance notes | Planned
Data Protection Lead / Operations | Data Understanding | Identify what personal data is processed, for what purpose, and where the most material risk sits. | Record of Processing Activities (RoPA) | Initial processing inventory and risk picture | ROPA entries, system notes, prioritised action list | Planned
Data Protection Lead / Management | Policy Baseline | Approve the policy baseline for protection, retention, rights handling, breach response, classification, and notices. | Data Protection Policy | Approved privacy policy baseline and outward-facing wording | Approvals, issue log, reviewed notice wording | Planned
Data Protection Lead / Functional Owners | Operational Privacy Controls | Adopt the procedures and templates for DSARs, breaches, retention, handling, and processor management. | DSAR Procedure; DSAR Request Form | Operational privacy workflows and escalation routes | Procedure sign-off, case handling records, workflow notes | Planned
Data Protection Lead / IT / Marketing | Records and Logs | Populate the ROPA, breach log, data sharing register, and consent and notice records used for accountability. | Record of Processing Activities (RoPA) | Live accountability records and privacy evidence base | Updated registers, notices, consent records, breach and request records | Planned
Data Protection Lead / Management | Compliance Review | Review whether rights handling, breach triage, notices, retention, and processor oversight are operating consistently. | DSAR Procedure | Privacy review outputs and remediation actions | Review notes, sample case outputs, action tracker | Planned