## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
GDPR sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Readiness
GDPR Readiness Checklist [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
GDPR ¦ Version 1.0 ¦ Practical implementation tracker
Domain / Control Area | Requirement / Objective | Key Actions | Related Document(s) | Suggested Owner | Status | Notes
Privacy Governance | Establish privacy ownership and governance oversight | Assign a privacy lead or DPO, confirm escalation routes, and approve the core privacy documents. | Data Protection Policy; Privacy Governance documents | Management / Privacy Lead | Not Started | Clarify controller and processor responsibilities.
Data Inventory | Understand what personal data is processed | Map key processing activities, systems, categories, and recipients. | ROPA; Data Flow Mapping Document | Privacy Lead / Operations | Not Started | Start with the most material processing first.
Lawful Basis and Notices | Align processing purposes with lawful basis and privacy notices | Review processing purposes, lawful bases, notices, and public-facing statements. | Privacy Notice Template; PII Processing Policy | Privacy Lead / Legal or Compliance | Not Started | Notices should match real data use.
Retention and Handling | Apply clear retention and data-handling rules | Set retention periods, disposal routes, and handling expectations for teams. | Data Retention Policy; Data Classification and Handling | Privacy Lead / IT / HR | Not Started | Retention should work operationally, not just on paper.
Data Subject Rights | Operate a rights-handling process | Tailor request handling steps, owners, SLAs, and communication routes. | Data Subject Rights Procedure; Request Handling Playbook | Privacy Lead | Not Started | Include verification and closure steps.
Third Parties | Manage processors and third-party data handling | Review supplier roles, DPAs, due diligence, and privacy responsibilities. | Third-Party Data Processing Policy; DPA Template | Procurement / Privacy Lead | Not Started | Prioritise high-risk suppliers.
Breach Handling | Prepare for privacy incidents and breaches | Confirm breach triage, escalation, notification decisions, and record keeping. | Privacy Incident and Breach Response Procedure | Privacy Lead / Security Lead | Not Started | Run at least one tabletop scenario.
Accountability | Create an evidence-backed privacy operating model | Maintain records, training, reviews, and periodic privacy assessments. | Privacy Audit and Monitoring Procedure; Compliance Review documents | Privacy Lead | Not Started | Documents must be paired with live records.