## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
ISO 27001 sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Overview
ISO 27001 Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
ISO 27001 ¦ Version 1.0 ¦ Sequenced implementation roadmap
Section | Detail
Framework | ISO 27001
Version | 1.0
Purpose | Practical rollout plan for implementing the pack as a working operating model.
How to use | Adapt owners, sequencing, and notes to the customer environment while keeping the implementation logic intact.
Key pack assets | Information Security Policy; Incident Response Procedure; Risk Register; Risk Treatment Plan
Roadmap notes | Governance and scope first, then risk-led control rollout, then evidence and formal review. ¦ Use the pack to build a working ISMS rather than a static document library.

## Roadmap
ISO 27001 Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
ISO 27001 ¦ Version 1.0 ¦ Sequenced implementation roadmap
Phase / Timeframe | Priority | Workstream | Task | Related Documents | Expected Output | Suggested Owner | Evidence to Retain | Status | Notes
Foundation / Scope / Governance | High | ISMS Foundation | Confirm ISMS scope, sponsorship, document ownership, and approval route. | Information Security Policy | Approved scope and governance baseline | Management / Information Security Officer | Scope approval, owner matrix, document approvals | Not Started | Keep scope manageable before widening it.
Foundation / Scope / Governance | High | Risk Management | Run the initial risk assessment and open treatment actions that shape rollout priorities. | Risk Register; Risk Treatment Plan | Initial risk view and treatment priorities | Information Security Officer | Risk assessments, register updates, treatment tracker | Not Started | Use risk outputs to sequence implementation work.
Core Policy Approval | High | Policy Baseline | Approve the core policy baseline for access, assets, incident response, suppliers, change, backup, and monitoring. | Information Security Policy | Approved policy baseline aligned to live practice | Management / Control Owners | Approval records, policy issue log, version-controlled set | Not Started | Do not publish untouched templates as operational policy.
Operational Procedure Adoption | High | Control Operation | Adopt the procedures that make policy requirements repeatable in day-to-day work. | Incident Response Procedure | Working procedures and clear evidence routes | Operational Leads / IT / Security | Procedure sign-off, workflow records, training notes | Not Started | Tie procedures to real tickets, logs, and reviews.
Register and Evidence Setup | High | Evidence Readiness | Populate the SoA, registers, logs, and audit artefacts needed for traceability and oversight. | Risk Register | Live control records and evidence structure | Information Security Officer / IT Lead | Completed registers, SoA entries, linked evidence locations | Not Started | Maintain evidence as controls go live, not at the end.
Review / Validation / Readiness | High | Assurance | Run internal audit activity, management review, and readiness validation. | Risk Treatment Plan | Review outputs, management decisions, and improvement actions | Compliance Lead / Management | Audit outputs, review minutes, action tracker | Not Started | Use findings to strengthen weak controls before external assurance.

## Owners_and_Evidence
ISO 27001 Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
ISO 27001 ¦ Suggested ownership and evidence planning
Suggested Owner | Workstream | Task Focus | Related Documents | Expected Output | Evidence to Retain | Status
Management / Information Security Officer | ISMS Foundation | Confirm ISMS scope, sponsorship, document ownership, and approval route. | Information Security Policy | Approved scope and governance baseline | Scope approval, owner matrix, document approvals | Planned
Information Security Officer | Risk Management | Run the initial risk assessment and open treatment actions that shape rollout priorities. | Risk Register; Risk Treatment Plan | Initial risk view and treatment priorities | Risk assessments, register updates, treatment tracker | Planned
Management / Control Owners | Policy Baseline | Approve the core policy baseline for access, assets, incident response, suppliers, change, backup, and monitoring. | Information Security Policy | Approved policy baseline aligned to live practice | Approval records, policy issue log, version-controlled set | Planned
Operational Leads / IT / Security | Control Operation | Adopt the procedures that make policy requirements repeatable in day-to-day work. | Incident Response Procedure | Working procedures and clear evidence routes | Procedure sign-off, workflow records, training notes | Planned
Information Security Officer / IT Lead | Evidence Readiness | Populate the SoA, registers, logs, and audit artefacts needed for traceability and oversight. | Risk Register | Live control records and evidence structure | Completed registers, SoA entries, linked evidence locations | Planned
Compliance Lead / Management | Assurance | Run internal audit activity, management review, and readiness validation. | Risk Treatment Plan | Review outputs, management decisions, and improvement actions | Audit outputs, review minutes, action tracker | Planned