## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
ISO 27001 sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Readiness
ISO 27001 Readiness Checklist [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
ISO 27001 ¦ Version 1.0 ¦ Practical implementation tracker
Domain / Control Area | Requirement / Objective | Key Actions | Related Document(s) | Suggested Owner | Status | Notes
ISMS Governance | Establish an operating ISMS baseline | Confirm scope, leadership sponsorship, document owners, and review cadence. | Information Security Policy; Pack Start Here Guide | Management / Security Lead | Not Started | Define what is in and out of scope early.
Risk Management | Operate a repeatable risk assessment and treatment method | Approve criteria, assess key risks, assign treatments, and track decisions. | Risk Management Policy; Risk Assessment Procedure; Risk Register | Security Lead | Not Started | Risk treatment should connect to live actions.
Control Ownership | Assign accountable owners to key controls | Map control areas to named owners and confirm review responsibilities. | Access Control Policy; Asset Management Policy; Supplier Security Policy | Security Lead / Functional Owners | Not Started | Avoid shared ownership without a clear lead.
Policy Adoption | Approve and issue the core governance documents | Tailor metadata, scope, systems, and approval routes before release. | Core policy set | Management | Not Started | Do not publish untouched templates.
Operational Procedures | Translate policy intent into live operating practice | Tailor procedures, agree evidence routes, and communicate working expectations. | Incident Response Procedure; Change Management Procedure; Access Provisioning Procedure | Operational Managers | Not Started | Procedures should match real workflows.
Awareness and Training | Build staff awareness of relevant obligations | Brief managers, train affected users, and maintain completion evidence. | Acceptable Use Policy; Guidance documents | People Lead / Security Lead | Not Started | Training should match role risk.
Internal Review | Plan internal audit and management review inputs | Schedule review activity, gather outputs, and track actions. | Management Review Template; Internal audit-related artefacts | Compliance Lead | Not Started | Review outputs should feed improvement actions.
Continual Improvement | Maintain the ISMS beyond initial rollout | Track incidents, findings, changes, and actions that require document updates. | Incident Response Policy; Risk Register; Review and maintenance sections | Security Lead | Not Started | Improvement should be visible in records and revisions.