## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
ISO/IEC 27701 Privacy Information Management System (PIMS) sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Overview
ISO/IEC 27701 Privacy Information Management System (PIMS) Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
ISO/IEC 27701 Privacy Information Management System (PIMS) ¦ Version 2.0 ¦ Sequenced implementation roadmap
Section | Detail
Framework | ISO/IEC 27701 Privacy Information Management System (PIMS)
Version | 2.0
Purpose | Practical rollout plan for implementing the pack as a working operating model.
How to use | Adapt owners, sequencing, and notes to the customer environment while keeping the implementation logic intact.
Key pack assets | Privacy Information Management Policy; Data Subject Rights Procedure; Data Processing Agreement (DPA) Template
Roadmap notes | Build privacy governance, records, rights handling, and processor oversight in a practical order. ¦ The pack supports the PIMS operating model; customer evidence and execution still matter.

## Roadmap
ISO/IEC 27701 Privacy Information Management System (PIMS) Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
ISO/IEC 27701 Privacy Information Management System (PIMS) ¦ Version 2.0 ¦ Sequenced implementation roadmap
Phase / Timeframe | Priority | Workstream | Task | Related Documents | Expected Output | Suggested Owner | Evidence to Retain | Status | Notes
Foundation / Scope / Governance | High | Privacy Governance | Confirm privacy scope, assign the privacy lead and supporting roles, and approve the governance baseline. | Privacy Information Management Policy | Approved privacy governance baseline | Management / Privacy Lead | Approval records, governance terms, role assignment confirmation | Not Started | Clarify controller and processor responsibilities early.
Foundation / Scope / Governance | High | Privacy Risk and Scope | Define priority processing activities, privacy risks, and rollout scope. | Data Subject Rights Procedure; Data Processing Agreement (DPA) Template | Initial privacy risk view and prioritised scope | Privacy Lead / Information Security Manager | Risk outputs, scoped processing inventory, action log | Not Started | Use risk and processing materiality to decide depth.
Core Policy Approval | High | Policy Baseline | Approve privacy governance, PII processing, classification, retention, and processor oversight policies. | Privacy Information Management Policy | Approved privacy policy baseline | Privacy Lead / Management | Policy approvals, tailoring notes, review schedule | Not Started | Keep wording consistent with actual systems and supplier use.
Operational Procedure Adoption | High | Operational Privacy Controls | Adopt procedures for DPIAs, rights handling, incidents, retention, and privacy monitoring. | Data Subject Rights Procedure | Operational privacy workflows and escalation routes | Privacy Lead / Functional Owners | Procedure approvals, case records, training outputs | Not Started | Teams need to know which privacy events trigger each process.
Register and Evidence Setup | High | Records and Evidence | Populate the ROPA, flow maps, DSAR, breach, retention, and processor records. | Data Processing Agreement (DPA) Template | Live privacy records and evidence routes | Privacy Lead / Procurement / Operations | Updated registers, log entries, processor reviews, mapping records | Not Started | Evidence should show current operation, not template availability.
Review / Validation / Readiness | High | PIMS Review | Run a privacy governance review covering control operation, evidence quality, unresolved risks, and improvement priorities. | Data Subject Rights Procedure; Privacy Risk Assessment Methodology | Privacy review outputs and next-cycle actions | Privacy Lead / Management | Review minutes, action tracker, evidence quality findings | Not Started | Align privacy governance with the actual delivery model.

## Owners_and_Evidence
ISO/IEC 27701 Privacy Information Management System (PIMS) Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
ISO/IEC 27701 Privacy Information Management System (PIMS) ¦ Suggested ownership and evidence planning
Suggested Owner | Workstream | Task Focus | Related Documents | Expected Output | Evidence to Retain | Status
Management / Privacy Lead | Privacy Governance | Confirm privacy scope, assign the privacy lead and supporting roles, and approve the governance baseline. | Privacy Information Management Policy | Approved privacy governance baseline | Approval records, governance terms, role assignment confirmation | Planned
Privacy Lead / Information Security Manager | Privacy Risk and Scope | Define priority processing activities, privacy risks, and rollout scope. | Data Subject Rights Procedure; Data Processing Agreement (DPA) Template | Initial privacy risk view and prioritised scope | Risk outputs, scoped processing inventory, action log | Planned
Privacy Lead / Management | Policy Baseline | Approve privacy governance, PII processing, classification, retention, and processor oversight policies. | Privacy Information Management Policy | Approved privacy policy baseline | Policy approvals, tailoring notes, review schedule | Planned
Privacy Lead / Functional Owners | Operational Privacy Controls | Adopt procedures for DPIAs, rights handling, incidents, retention, and privacy monitoring. | Data Subject Rights Procedure | Operational privacy workflows and escalation routes | Procedure approvals, case records, training outputs | Planned
Privacy Lead / Procurement / Operations | Records and Evidence | Populate the ROPA, flow maps, DSAR, breach, retention, and processor records. | Data Processing Agreement (DPA) Template | Live privacy records and evidence routes | Updated registers, log entries, processor reviews, mapping records | Planned
Privacy Lead / Management | PIMS Review | Run a privacy governance review covering control operation, evidence quality, unresolved risks, and improvement priorities. | Data Subject Rights Procedure; Privacy Risk Assessment Methodology | Privacy review outputs and next-cycle actions | Review minutes, action tracker, evidence quality findings | Planned