## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
PCI-DSS sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Overview
PCI-DSS Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
PCI-DSS ¦ Version 1.0 ¦ Sequenced implementation roadmap
Section | Detail
Framework | PCI-DSS
Version | 1.0
Purpose | Practical rollout plan for implementing the pack as a working operating model.
How to use | Adapt owners, sequencing, and notes to the customer environment while keeping the implementation logic intact.
Key pack assets | Information Security Policy; Vulnerability Scanning Procedure; CDE Asset Inventory; Access Request Form
Roadmap notes | Scope, ownership, and evidence planning first. ¦ The pack supports the PCI operating model; it does not itself perform technical remediation or testing.

## Roadmap
PCI-DSS Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
PCI-DSS ¦ Version 1.0 ¦ Sequenced implementation roadmap
Phase / Timeframe | Priority | Workstream | Task | Related Documents | Expected Output | Suggested Owner | Evidence to Retain | Status | Notes
Foundation / Scope / Governance | High | CDE Scope | Define the cardholder data environment, segmentation assumptions, and critical dependencies before tailoring the pack. | Information Security Policy; Access Request Form | Agreed CDE scope and owner map | Management / Technical Lead | Scope notes, architecture diagrams, service inventory, approval records | Not Started | Poor scoping creates weak evidence later.
Core Policy Approval | High | PCI Governance Baseline | Approve the baseline for network security, access control, encryption, and vulnerability management. | Information Security Policy | Approved PCI-oriented governance baseline | Compliance Lead / Technical Lead | Policy approvals, owner assignments, issue log | Not Started | Keep technical owner accountability explicit by control area.
Operational Procedure Adoption | High | Control Operation | Adopt procedures for scanning, patching, logging review, access control, and incident handling around the in-scope environment. | Vulnerability Scanning Procedure | Repeatable PCI operating procedures | Technical Lead / IT Lead | Scan records, review logs, approved procedure set, incident workflow records | Not Started | Use real technical workflows and evidence sources.
Register and Evidence Setup | High | Evidence Readiness | Create the evidence model for assets, access reviews, vulnerability actions, logging review, and supporting diagrams. | CDE Asset Inventory; Access Request Form | Evidence repository approach and live PCI tracking artefacts | Compliance Lead / Technical Lead | Asset inventory, access review outputs, vulnerability tracker, diagrams | Not Started | Evidence should be refreshable throughout the year.
Review / Validation / Readiness | High | PCI Readiness Review | Review scope assumptions, technical evidence quality, logging discipline, access controls, and remediation cadence. | CDE Asset Inventory | PCI readiness review and remediation priorities | Compliance Lead / Management | Review notes, remediation tracker, scope sign-off | Not Started | Be explicit where customer technical implementation is still required.

## Owners_and_Evidence
PCI-DSS Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
PCI-DSS ¦ Suggested ownership and evidence planning
Suggested Owner | Workstream | Task Focus | Related Documents | Expected Output | Evidence to Retain | Status
Management / Technical Lead | CDE Scope | Define the cardholder data environment, segmentation assumptions, and critical dependencies before tailoring the pack. | Information Security Policy; Access Request Form | Agreed CDE scope and owner map | Scope notes, architecture diagrams, service inventory, approval records | Planned
Compliance Lead / Technical Lead | PCI Governance Baseline | Approve the baseline for network security, access control, encryption, and vulnerability management. | Information Security Policy | Approved PCI-oriented governance baseline | Policy approvals, owner assignments, issue log | Planned
Technical Lead / IT Lead | Control Operation | Adopt procedures for scanning, patching, logging review, access control, and incident handling around the in-scope environment. | Vulnerability Scanning Procedure | Repeatable PCI operating procedures | Scan records, review logs, approved procedure set, incident workflow records | Planned
Compliance Lead / Technical Lead | Evidence Readiness | Create the evidence model for assets, access reviews, vulnerability actions, logging review, and supporting diagrams. | CDE Asset Inventory; Access Request Form | Evidence repository approach and live PCI tracking artefacts | Asset inventory, access review outputs, vulnerability tracker, diagrams | Planned
Compliance Lead / Management | PCI Readiness Review | Review scope assumptions, technical evidence quality, logging discipline, access controls, and remediation cadence. | CDE Asset Inventory | PCI readiness review and remediation priorities | Review notes, remediation tracker, scope sign-off | Planned