## READ_ME_SAMPLE
SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE
SOC 2 sample / preview workbook
This workbook is a preview version and may be abbreviated. The full purchased pack includes the complete editable set and deeper implementation-ready content.
Do not rely on this sample as an operationally complete deliverable.

## Overview
SOC 2 Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
SOC 2 ¦ Version 2.0 ¦ Sequenced implementation roadmap
Section | Detail
Framework | SOC 2
Version | 2.0
Purpose | Practical rollout plan for implementing the pack as a working operating model.
How to use | Adapt owners, sequencing, and notes to the customer environment while keeping the implementation logic intact.
Key pack assets | Information Security Policy; Access Control Policy; HR Joiner Mover Leaver Procedure
Roadmap notes | Move from a policy bundle to a sustained SOC 2-oriented control environment. ¦ Design for evidence over time, not one-off readiness screenshots.

## Roadmap
SOC 2 Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
SOC 2 ¦ Version 2.0 ¦ Sequenced implementation roadmap
Phase / Timeframe | Priority | Workstream | Task | Related Documents | Expected Output | Suggested Owner | Evidence to Retain | Status | Notes
Foundation / Scope / Governance | High | Control Environment | Confirm Trust Services Criteria scope, policy ownership, management oversight, and assurance priorities. | Information Security Policy | Approved control-environment baseline and named owners | Management / Compliance Manager | Owner matrix, approvals, management scope notes | Not Started | Start with Security and only extend scope where commercially relevant.
Core Policy Approval | High | Policy Baseline | Approve the policy baseline for access, change, incident response, logging, backup, risk, and vendor oversight. | Access Control Policy | Approved SOC 2 policy baseline | Compliance Manager / Functional Owners | Approved policy set, issue log, owner sign-off | Not Started | Keep commitments aligned to the actual operating model.
Operational Procedure Adoption | High | Control Operation | Adopt the procedures behind access reviews, JML handling, change approvals, vendor reviews, and monitoring. | HR Joiner Mover Leaver Procedure | Operational control workflows and evidence cadence | IT Manager / Head of Engineering / Procurement Lead | Procedure approvals, review outputs, tickets, vendor review records | Not Started | Design for repeatable evidence over time.
Register and Evidence Setup | High | Evidence Management | Set up the evidence model for access reviews, changes, monitoring, incidents, asset records, and vendor governance. | Relevant pack documents | Evidence ownership map and live control records | Compliance Manager / IT Manager | Register updates, evidence repository plan, recurring review schedule | Not Started | Evidence should be attributable, retained, and easy to refresh.
Review / Validation / Readiness | High | Readiness Review | Review whether key controls are operating consistently and whether evidence is retained at the right cadence. | Information Security Policy; Access Control Policy; HR Joiner Mover Leaver Procedure | Readiness review, remediation backlog, and ongoing assurance rhythm | Compliance Manager / Management | Readiness review notes, remediation tracker, management reporting plan | Not Started | Look for sustained control operation, not isolated examples.

## Owners_and_Evidence
SOC 2 Implementation Roadmap [SAMPLE / PREVIEW / NOT FOR OPERATIONAL USE]
SOC 2 ¦ Suggested ownership and evidence planning
Suggested Owner | Workstream | Task Focus | Related Documents | Expected Output | Evidence to Retain | Status
Management / Compliance Manager | Control Environment | Confirm Trust Services Criteria scope, policy ownership, management oversight, and assurance priorities. | Information Security Policy | Approved control-environment baseline and named owners | Owner matrix, approvals, management scope notes | Planned
Compliance Manager / Functional Owners | Policy Baseline | Approve the policy baseline for access, change, incident response, logging, backup, risk, and vendor oversight. | Access Control Policy | Approved SOC 2 policy baseline | Approved policy set, issue log, owner sign-off | Planned
IT Manager / Head of Engineering / Procurement Lead | Control Operation | Adopt the procedures behind access reviews, JML handling, change approvals, vendor reviews, and monitoring. | HR Joiner Mover Leaver Procedure | Operational control workflows and evidence cadence | Procedure approvals, review outputs, tickets, vendor review records | Planned
Compliance Manager / IT Manager | Evidence Management | Set up the evidence model for access reviews, changes, monitoring, incidents, asset records, and vendor governance. | Relevant pack documents | Evidence ownership map and live control records | Register updates, evidence repository plan, recurring review schedule | Planned
Compliance Manager / Management | Readiness Review | Review whether key controls are operating consistently and whether evidence is retained at the right cadence. | Information Security Policy; Access Control Policy; HR Joiner Mover Leaver Procedure | Readiness review, remediation backlog, and ongoing assurance rhythm | Readiness review notes, remediation tracker, management reporting plan | Planned